## Work Items
Issue Key | Work Item | Epic | Owner | Status | Priority | Start Date | Due Date | Dependency | Blocker | Next Action | Milestone Confidence
SCRUM-11 | Define functional requirements and success metrics | Discovery & Requirements | TPM (Simulation) | To Do | High | 2026-10-14 | 2026-10-15 | None | None | Confirm scope and success metrics | High
SCRUM-12 | Map AI workflow and exception paths | Workflow & Integration Design | Technical Owner (Simulation) | In Progress | High | 2026-10-14 | 2026-10-16 | SCRUM-11 | Requirements review pending | Follow up with requirements owner; confirm review date | Low
SCRUM-13 | Define AI classification and review rules | AI Classification & Response Drafting | AI Engineer (Simulation) | To Do | High | 2026-10-15 | 2026-10-19 | SCRUM-12 | None | Define classification rules and human-review thresholds | Medium
SCRUM-14 | Define integration failure and retry handling | Testing, Reliability & Readiness | Integration Engineer (Simulation) | To Do | High | 2026-10-15 | 2026-10-19 | SCRUM-12 | None | Document retry limits and duplicate-prevention tests | Medium
SCRUM-15 | Build the delivery health tracker | Delivery Monitoring & Handover | TPM (Simulation) | To Do | High | 2026-10-14 | 2026-10-20 | None | None | Validate tracker formulas and reporting view | High

## Progam Health
Total Work Items | Overdue Open Items | Blocked Open Items
5 | 0 | 1